## Sheet1
Big Data Project Tasks | Spring 2014
Tasks | Name | Date | Complete
Get zip code-county mapping and write logic to lookup based on report from inpatient data | Chen | 2014-04-07 | X
Run MapReduce project on HPC with Inpatient Data | Chris | 2014-04-11
Breakdown existing census employment data by fields and determine relevant metric | Chen | 2014-04-17
Get bulk unemployment data with job distributions | Chris, Chen, George
Generate charts from reported analytic | George | 2014-04-10
Explore visualizations using d3 or other libraries | George
Analyze employment data with Pig
Explore CDC dataset for more health detail | George | 2014-04-10
Develop paper draft based on the project proposal | Chris | 2014-04-07 | X
Develop concrete results and commit to findings |  | 2014-04-21