## Sheet1
Big Data Project Tasks | Spring 2014
Tasks | Name | Date | Complete
Get zip code-county mapping and write logic to lookup based on report from inpatient data | Khen | 2014-04-07 | X
Run MapReduce project on HPC with Inpatient Data | Chris | 2014-04-11 | X
Get bulk unemployment data with job distributions | Chris, Khen, George | 2014-04-10 | N/A
Explore visualizations using d3 or other libraries | George | 2014-04-17 | X
Analyze employment data with Pig | Khen, Chris | 2014-04-17 | X
Explore CDC dataset for more health detail | George | 2014-04-10 | N/A
Develop paper draft based on the project proposal | Chris | 2014-04-07 | X
Breakdown existing census employment data by fields and consolidate into combined results | Chen | 2014-04-22
Develop concrete results and commit to findings | ! | 2014-04-23
Choose functional attributes for regression (Weka/STATA) | George | 2014-04-24
Generate charts from reported analytic | George | 2014-04-28
Update paper with draft of findings (RESULTS) | Chris | 2014-05-01
Update paper with draft of future work |  | 2014-05-01
Update paper with draft of Conclusions |  | 2014-05-01
Presentation Slides and draft script | George | 2014-05-01
Presentation | Chris, Khen, George | 2014-05-08